1. Contact Details

Contact Name: Michelle Mitchell

Name and Address of Organisation (including Postcode)

INSPIREYOUTH TYNE & WEAR – Formally PLAYinNEWCASTLE

CARNEGIE BUILDING

ATKINSON ROAD

NEWCASTLE

NE4 8XS

Post Code

1. Approximately how many people within the Parish Council area benefitted from the Grant? 180
2. Which areas of the Parish benefitted from the grant?

NEWBIGGIN HALL

1. Who benefitted from the grant

Please tick relevant box below

|  |  |
| --- | --- |
| Description | Total Number |
| Children under 16 | 162 |
| 17 – 25 year olds | 18 |
| 26 – 54 year olds |  |
| People over 55 |  |

1. Please Provide a breakdown of costs

|  |  |
| --- | --- |
| Description | Actual cost |
| DETACHED 2 SESSIONS PER WEEK X12 WEEKS | £3456.00 |
| SPECIALISED MENTORING X 12 WEEKS | £1920.00 |
| INTERS OUTDOOR SESSIONS X 12 WEEKS | £2160.00 |
| MATERIALS & SNACKS | £480.00 |
| ACTIVITY PACKS | £600.00 |
|  | £ |
|  | £ |
| TOTAL COST | £8616.00 |

1. Describe the activity and when it happened

|  |  |  |
| --- | --- | --- |
|  | Activity | Date |
| 1 | Detached sessions twice a week – Monday & Tuesday. | December - January – February - March |
| 2 | Specialised Mentoring various days of the week with the young people. | December - January – February - March |
| 3 | Inters sessions – Wednesday nights | December - January – February - March |
| 4 | Activity packs delivered weekly | December - January – February - March |
| 5 |  |  |

7. How successful was the project in achieving the anticipated outcomes?

Due to the most recent lockdown, we adapted the services we deliver to the young people to follow government guidelines but to ensure the young people were still able to access support and guidance. We were unable to work with the Music Studio as they were unable to deliver the social distance ruling with the young people.

The project was successful, we delivered an extra evening of detached due to not being able to do sessions with the Seniors, staff were able to engage with the young people, talk to them about their issues, support them with access to education and other services, remind them of the lockdown rules and deter them from ASB.

We have delivered Specialised Mentoring to young people who have been referred into the project by the Police – This service is working extremely well, we have assisted young people to get back into education, access fitness sessions to help overcome mental health and anxiety, work with their families to ensure they get the correct support and guidance. Importantly mentored them to begin to overcome their traumas and ACE’s.

The Inters sessions on the courts was delivered following COVID guidelines – young people had to be invited to attend the sessions and we were limited to 15 at each session but the outcomes were fantastic, all those who attended engaged and took a lot away from the sessions. At every session we gave them something to eat and resources to take away so whilst at home they were able to do activities which covered mental health and other issues.

Overall, we have had a successful project and continue to deliver in Newbiggin Hall as there is a need in the area – the ASB has risen, and we are working with the Police and other services to overcome this and give the young people involved an opportunity to deter from criminality with positive and productive activities. Once we are out of lockdown, we will work with the Music Studio and provide Senior sessions.